## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status | Progress (%)
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Project Manager | Completed | 100%
Requirement Gathering | 2024-04-02 | 2024-04-10 | 9 | High | Business Analyst | In Progress | 60%
Design Phase (UI/UX) | 2024-04-11 | 2024-04-25 | 15 | Medium | UX Designer | Not Started | 0%
Development Phase | 2024-05-01 | 2024-06-30 | 60 | High | Development Team | Not Started | 0%
Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 | High | QA Lead | Not Started | 0%
Go-Live & Deployment | 2024-08-01 | 2024-08-05 | 5 | High | IT Operations | Not Started | 0%