## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible Person | Notes
Project Planning & Scope Definition | 2024-04-01 | 2024-04-07 | 7 | High | In Progress | Jane Smith | Finalize scope, define deliverables, and secure stakeholder approval.
Market Research & Competitor Analysis | 2024-04-08 | 2024-04-15 | 8 | High | Not Started | Alex Johnson | Collect data from 3 key competitors and present findings.
Design Phase (Wireframes & Mockups) | 2024-04-16 | 2024-05-03 | 18 | Medium | Planned | Maya Patel | Create user flows and interactive prototypes for core features.
Development & Coding | 2024-05-04 | 2024-06-30 | 68 | High | Not Started | David Lee | Backend and frontend development in full sync with design specs.
Testing & Quality Assurance | 2024-07-01 | 2024-07-15 | 15 | Medium | Planned | Sophia Kim | Conduct functional and usability testing with real users.
User Training & Go-Live | 2024-07-16 | 2024-07-25 | 10 | Low | Not Started | Rachel Wong | Train end-users and deploy system to production.
Post-Launch Review & Feedback | 2024-07-26 | 2024-08-05 | 10 | Low | Planned | Team Lead | Gather feedback and document lessons learned for future projects.