## Worksheet
Project Name | Quarter | Start Date | End Date | Primary Owner | Status | Time Allocation (hrs/week) | Key Milestones | Progress (%) | Notes
Product Launch Q3 | Q3 2024 | 2024-07-01 | 2024-09-30 | Sarah Johnson | On Track | 15 | Design Finalized, Beta Testing Complete | 85% | No critical delays; team aligned.
Customer Onboarding System | Q3 2024 | 2024-08-15 | 2024-11-15 | Michael Chen | In Progress | 10 | User Flow Approval, MVP Build | 40% | Awaiting stakeholder feedback.
Marketing Campaign Revamp | Q4 2024 | 2024-10-01 | 2024-12-31 | Emma Davis | Planned | 8 | Audience Research, Creative Design Phase | 0% | Budget approved; kickoff scheduled.
Team Training & Development | Q4 2024 | 2024-11-05 | 2024-12-31 | James Wilson | Pending Approval | 5 | Workshop Schedule, Content Development | 0% | Needs manager sign-off.