## Worksheet
Task | Start Date | End Date | Estimated Time (hrs) | Actual Time (hrs) | Status | Priority | Responsible Person
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 2.5 | 2.5 | Completed | High | John Doe
Market Research Phase | 2024-04-02 | 2024-04-10 | 15 | 13.5 | In Progress | High | Sarah Lee
Product Design Finalization | 2024-04-11 | 2024-04-18 | 20 | 18.7 | In Progress | Medium | Mike Chen
Development Sprint 1 | 2024-04-19 | 2024-04-25 | 35 | 32.1 | In Progress | High | David Kim
Testing & Quality Assurance | 2024-04-26 | 2024-05-03 | 30 | - | Not Started | High | Lisa Wong