## Worksheet
Task | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
Market Research & Competitor Analysis | Alex Rivera | 2024-03-15 | 2024-03-25 | In Progress | High | 16 | 12 | 75%
Product Roadmap Finalization | Samantha Lee | 2024-03-20 | 2024-04-10 | Not Started | High | 24 | 0 | 0%
UI/UX Wireframe Design | Jordan Patel | 2024-03-25 | 2024-04-15 | In Progress | Medium | 32 | 20 | 62.5%
Development Sprint Planning | Morgan Clark | 2024-04-01 | 2024-05-31 | Not Started | High | 80 | 0 | 0%
Customer Feedback Loop Setup | Taylor Kim | 2024-04-10 | 2024-05-15 | Not Started | Medium | 18 | 0 | 0%