## Worksheet
Task | Assigned To | Start Date | End Date | Estimated Hours | Actual Hours | Status | Priority | Dependencies
Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-01 | 2 | 2 | Completed | High
Requirements Gathering | Product Owner | 2024-04-02 | 2024-04-10 | 16 | 15 | In Progress | High | Kickoff Meeting
UI/UX Design Phase | Design Team | 2024-04-11 | 2024-04-25 | 30 | 18 | In Progress | Medium | Requirements Finalized
Development Sprint 1 | Engineering Team | 2024-04-26 | 2024-05-10 | 80 | 65 | In Progress | High | UI/UX Design Complete
Testing & Quality Assurance | QA Team | 2024-05-11 | 2024-05-30 | 40 | 35 | Not Started | High | Development Sprint 1 Complete
Final Review & Deployment | Project Manager | 2024-06-01 | 2024-06-05 | 10 |  | Not Started | High | Testing Complete