## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Priority | Responsible Person | Progress (%)
Project Planning & Scope Definition | 2024-04-01 | 2024-04-10 | 10 | In Progress | High | Alice Johnson | 75%
Market Research & Analysis | 2024-04-11 | 2024-04-25 | 15 | Planned | Medium | Bob Smith | 0%
Design Phase (UI/UX) | 2024-04-26 | 2024-05-15 | 20 | Not Started | High | Charlie Brown | 0%
Development & Coding | 2024-05-16 | 2024-06-30 | 45 | Planned | High | Diana Lee | 0%
Testing & Quality Assurance | 2024-07-01 | 2024-07-15 | 15 | Not Started | Medium | Eve Wilson | 0%
Deployment & Launch | 2024-07-16 | 2024-07-20 | 5 | Planned | High | Frank Moore | 0%