## Worksheet
Task | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress %
Project Planning Meeting | John Doe | 2024-04-01 | 2024-04-01 | Completed | Medium | 2 | 2 | 100%
Requirement Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | In Progress | High | 10 | 6.5 | 65%
Design Phase | Alex Chen | 2024-04-11 | 2024-04-25 | Not Started | High | 15 | 0 | 0%
Development Phase | Sam Lee | 2024-04-26 | 2024-05-15 | Scheduled | Medium | 40 | 0 | 0%
Testing & QA | Mia Rodriguez | 2024-05-16 | 2024-05-31 | Not Started | High | 20 | 0 | 0%
Final Review & Deployment | Team Lead | 2024-06-01 | 2024-06-05 | Planned | Medium | 5 | 0 | 0%