## Worksheet
Travel Planning Business Plan
Office Use Template ¦ Version 1.0
Item | Description | Expected Outcome / Goal | Timeline (Start - End) | Budget (USD) | Status
Market Research | Analyze target markets, travel trends, and competitor offerings. | Identify 3 key market segments for service customization. | Jan 01 - Jan 15 | $2,500 | In Progress
Service Development | Design customizable travel packages: Business, Leisure, and Group Travel. | Launch 3 pilot travel packages by Q2. | Jan 16 - Mar 31 | $8,000 | On Track
Website & Booking System | Develop user-friendly website with real-time booking and payment integration. | Live website launch by April 15. | Feb 01 - Apr 15 | $20,000 | Delayed
Marketing Campaign (Digital) | Create digital ads, social media content, and email newsletters. | Reach 50K impressions in Q2; acquire 500 new leads. | Mar 01 - Jun 30 | $6,500 | Not Started
Partnership Development | Negotiate with hotels, airlines, and local tour operators. | Secure 10 strategic partnerships by May 31. | Feb 01 - May 31 | $4,200 | In Progress
Customer Support Team | Hire and train 5 customer support staff. | Full team operational by April 30. | Mar 01 - Apr 30 | $12,000 | On Track
Total Budget: |  |  |  | $53,200