## Worksheet
Travel Planning - Business Plan - Planning View
Phase | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
Planning & Research | Define travel objectives, target destinations, and key stakeholders | Project Manager | 2023-10-01 | 2023-10-15 | In Progress | $5,000.00
Route Design | Create optimized travel routes with key stops and logistics planning | Logistics Coordinator | 2023-10-16 | 2023-10-25 | To Do | $8,500.00
Vendor Selection | Select and contract transportation, accommodation, and activity providers | Procurement Team | 2023-10-26 | 2023-11-05 | To Do | $45,000.00
Itinerary Finalization | Compile full itinerary with detailed schedules and emergency protocols | Travel Planner | 2023-11-06 | 2023-11-15 | To Do | $4,800.00
Client Communication & Approval | Share proposed plan with stakeholders for feedback and final sign-off | Client Relations Manager | 2023-11-16 | 2023-11-25 | To Do | $3,000.00
Implementation & Monitoring | Execute travel plan and monitor progress in real-time during trip | Field Operations Team | 2023-11-26 | 2024-01-31 | To Do | $85,000.00
Post-Trip Review & Reporting | Conduct debriefing sessions and deliver comprehensive performance report | Project Analyst | 2024-02-01 | 2024-02-15 | To Do | $7,500.00
Total Estimated Budget: | [5 empty] | $163,800.00