## Worksheet
Travel Planning Business Plan
Weekly Overview Template
Week Starting | Objective / Goal | Key Activities | Status | Budget Allocated (USD) | Budget Used (USD) | Risk Factors | Milestone Achieved?
2024-04-01 | Finalize Q2 travel package designs | Conduct market research, review customer feedback, develop 3 new itineraries | In Progress | $15,000.00 | $8,500.00 | Supplier delays may impact timeline | No
2024-04-15 | Secure partnerships with 3 new tour providers | Contact potential partners, negotiate contracts, conduct background checks | Completed | $6,000.00 | $5,750.00 | Higher negotiation demands from providers | Yes
2024-14-29 | Launch marketing campaign for summer packages | Create digital ads, email sequences, social media content, track engagement metrics | To Do | $8,500.00 | $0.00 | Ad spend exceeding targets possible due to high competition | No
© 2024 Travel Planning Business ¦ Weekly Plan Template ¦ Confidential