## Worksheet
Travel Planning Gantt Chart - Business Use
Task | Start Date | End Date | Duration (Days) | Status | Responsible Team
Destination Research & Selection | 2023-10-05 | 2023-10-12 | 8 |  | Strategy & Planning Team
Travel Itinerary Drafting | 2023-10-13 | 2023-10-18 | 6 |  | Operations Team
Flight & Accommodation Booking | 2023-10-19 | 2023-10-25 | 7 |  | Finance & Logistics Team
Pre-Departure Review Meeting (Milestone)
Travel Insurance & Documentation | 2023-10-26 | 2023-10-31 | 6 |  | Compliance Team
On-Site Coordination Setup | 2023-11-01 | 2023-11-05 | 5 |  | Field Operations Team
Departure Day (Milestone)
Post-Trip Debrief & Reporting | 2023-11-10 | 2023-11-17 | 8 |  | All Teams