## Travel Planning Gantt Chart
Travel Planning Gantt Chart (Extended Version)
Task | Start Date | End Date | Duration (Days) | Status | % Complete
Travel Planning & Research | 2024-04-01 | 2024-04-15 | 15 | In Progress | 75%
Destination Research | 2024-04-01 | 2024-04-05 | 5 | Completed | 100%
Budget Estimation | 2024-04-06 | 2024-04-15 | 10 | In Progress | 80%
Planning Phase Complete (Milestone)
Flight & Accommodation Booking | 2024-04-16 | 2024-05-10 | 25 | In Progress | 68%
Flight Booking | 2024-04-16 | 2024-04-30 | 15 | In Progress | 85%
Hotel Reservation | 2024-05-01 | 2024-05-10 | 10 | In Progress | 68%
Bookings Confirmed (Milestone)
Travel Documents & Insurance | 2024-05-11 | 2024-06-05 | 25 | In Progress | 48%
Passport & Visa Checks | 2024-05-11 | 2024-05-18 | 8 | In Progress | 95%
Travel Insurance Purchase | 2024-05-19 | 2024-05-31 | 13 | In Progress | 60%
Documents Ready (Milestone)
Travel Execution & Sightseeing | 2024-06-06 | 2024-07-15 | 40 | Scheduled | 5%
Arrival & Check-in | 2024-06-06 | 2024-06-15 | 10 | Scheduled | 5%
Daily Itinerary Execution | 2024-06-16 | 2024-07-15 | 30 | Scheduled | 5%
Trip Complete (Milestone)
Travel Debrief & Photo Review | 2024-07-16 | 2024-08-15 | 31 | Scheduled | 0%
Photos & Memory Compilation | 2024-07-16 | 2024-08-15 | 31
Post-Trip Review Complete (Milestone)
Note: This is an extended Gantt chart template for travel planning. Dates and progress are illustrative.