## Worksheet
Travel Planning Gantt Chart
Global Business Trip – Q3 2024
Task Name | Start Date | End Date | Status | Progress
1. Destination & Itinerary Planning | Jul 01, 2024 | Jul 07, 2024 | Completed
2. Flights & Transportation Booking | Jul 08, 2024 | Jul 15, 2024 | Completed
3. Hotel & Accommodation Reservations | Jul 08, 2024 | Jul 15, 2024 | Completed
4. Visa Application & Documents | Jul 16, 2024 | Jul 25, 2024 | In Progress
5. Client & Partner Meetings | Jul 26, 2024 | Aug 03, 2024 | Not Started
6. On-Site Business Engagements | Aug 04, 2024 | Aug 12, 2024 | Not Started
7. Debrief & Report Submission | Aug 13, 2024 | Aug 20, 2024 | Not Started
M1. Final Approval & Travel Clearance | Jul 07, 2024 | Jul 07, 2024 | Completed
M2. Visa Approval Confirmation | Jul 25, 2024 | Jul 25, 2024 | Not Started
M3. Final Travel Debrief & Feedback | Aug 20, 2024 | Aug 20, 2024 | Not Started
Last updated: June 30, 2024