## Worksheet
Travel Planning - Manager View Gantt Chart
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status | Progress
Destination Research & Selection | 2024-04-05 | 2024-04-15 | 11 | Market Research Team | Pending
Itinerary Planning & Approval | 2024-04-16 | 2024-04-30 | 15 | Travel Coordination Team | In Progress
Accommodation Booking | 2024-04-18 | 2024-05-05 | 18 | Logistics Team | In Progress
Flight Reservations | 2024-04-20 | 2024-05-15 | 36 | Air Travel Team | In Progress
Insurance & Documentation | 2024-04-25 | 2024-05-10 | 16 | Compliance Team | In Progress
Local Transportation Arrangements | 2024-05-01 | 2024-05-18 | 18 | Logistics Team | Pending
Final Travel Package Delivery | 2024-05-18 | 2024-05-19 | 2 | Project Manager | Pending
Travel Launch Event (Milestone)