## Worksheet
Travel Planning Gantt Chart - Report Version
Task ID | Task Description | Start Date | End Date | Status | Duration (Days) | Progress (%)
Destination Research & Planning
TR-001 | Research Travel Destinations | 2023-10-15 | 2023-10-25 | In Progress | 11
TR-002 | Compare Visa Requirements | 2023-10-18 | 2023-10-27 | In Progress | 10
Booking & Logistics
TR-003 | Book Flights (Round Trip) | 2023-10-28 | 2023-11-05 | Pending | 9
TR-004 | Reserve Accommodations | 2023-11-01 | 2023-11-15 | Pending | 15
On-Site Planning & Activities
TR-005 | Plan Local Transportation | 2023-11-10 | 2023-11-20 | Pending | 11
TR-006 | Milestone: Travel Itinerary Finalized | 2023-11-25 | 2023-11-25 | To Do | 1
Final Preparations & Departure
TR-007 | Prepare Travel Documents | 2023-11-26 | 2023-11-30 | Pending | 5
TR-008 | Packing & Final Checks | 2023-12-01 | 2023-12-04 | Pending | 4
TR-009 | Milestone: Departure Day - Travel Begins | 2023-12-05 | 2023-12-05 | To Do | 1
Report generated on¦ Travel Planning Gantt Chart - Version 2.1