## Worksheet
Travel Planning Project Plan - Advanced Template
Task ID | Task Description | Owner | Start Date | End Date | Status | % CompleteMilestone?
P1.0 | Initial Planning & Goal Setting | Project Manager | 2024-04-05 | 2024-04-15 | Completed | 100% | Yes
P1.1 | Define Travel Objectives & Budget Range | Project Manager | 2024-04-05 | 2024-04-10 | Completed | 100% | No
P1.2 | Finalize Destination & Travel Dates | Travel Coordinator | 2024-04-11 | 2024-04-15 | Completed | 100% | No
P2.0 | Logistics and Booking Phase | Travel Coordinator | 2024-04-16 | 2024-05-15 | Completed | 100% | Yes
P2.1 | Book Flights & Accommodations | Travel Coordinator | 2024-04-16 | 2024-05-03 | Completed | 100% | No
P2.2 | Arrange Transportation (Airport Transfers) | Logistics Assistant | 2024-05-04 | 2024-05-10 | Completed | 100% | No
P2.3 | Book Local Activities & Tours | Travel Coordinator | 2024-05-11 | 2024-05-15 | Completed | 100% | No
P3.0 | Documentation & Pre-Departure Prep | Project Manager | 2024-05-16 | 2024-06-15 | Completed | 100% | Yes
P3.1 | Generate Travel Itinerary & Maps | Travel Coordinator | 2024-05-16 | 2024-05-25 | Completed | 100% | No
P3.2 | Prepare Travel Documents (Passports, Visas) | All Travelers | 2024-05-26 | 2024-06-15 | Completed | 100% | No
P4.0 | Final Checks & Departure Readiness | Project Manager | 2024-06-16 | Completed | Final phase - Travel begins on 2024-07-15.
P4.1 | Confirm All Bookings & Itinerary Accuracy | Travel Coordinator | Finalized by 2024-06-30 |  | Completed | 100% | No
P4.2 | Final Health & Safety Briefing (Vaccinations, Insurance) | Health Officer | Completed by 2024-06-15 |  | Completed | 100% | No
P5.0 | On-the-Road Monitoring & Adjustments | Ongoing from 2024-07-15 until return on 2024-08-15.
P5.1 | Real-Time Travel Updates & Issues Management | Project Manager | Active during travel period |  |  | In Progress | 70% | No
P6.0 | Post-Trip Evaluation & Reporting | Scheduled after return (2024-08-16 to 2024-09-15)
P6.1 | Collect Feedback from Travelers | Project Manager | Target: 2024-08-16 to 2024-08-31 |  | Delayed | 35% | No
P6.2 | Compile Final Report & Lessons Learned | Project Manager | Target: 2024-09-01 to 2024-09-15 |  | Delayed | 15% | No