## Travel Planning Project Plan
Travel Planning Project Plan
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
T001 | Define Travel Objectives & Budget | Project Manager | 2024-10-15 | 2024-10-18 | In Progress | $5,000.00
T002 | Research Destinations & Itineraries | Travel Coordinator | 2024-10-19 | 2024-10-25 | To Do | $850.00
T003 | Book Flights & Accommodations | Travel Coordinator | 2024-10-26 | 2024-11-03 | To Do | $3,750.00
T004 | Arrange Local Transportation & Tours | Local Guide Team | 2024-11-04 | 2024-11-10 | To Do | $950.00
T005 | Obtain Travel Insurance & Visas | Administrative Assistant | 2024-11-11 | 2024-11-15 | To Do | $300.00
T006 | Finalize Itinerary & Share with Team | Project Manager | 2024-11-16 | 2024-11-18 | To Do | $0.00
T007 | Pre-Departure Briefing & Documentation Check | Project Manager | 2024-11-19 | 2024-11-20 | To Do | $50.00
Total Project Budget: | [5 empty] | $11,900.00