## Travel Planning - Client View
Travel Planning Project Plan - Client View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Budget (USD)
T1001 | Destination Research & Selection | Travel Coordinator A | 2024-07-15 | 2024-07-25 | Pending | $1,500.00
T1002 | Flight Booking & Confirmations | Travel Coordinator B | 2024-07-18 | 2024-07-30 | In Progress | $6,850.00
T1003 | Hotel Reservations & Contract Signing | Travel Coordinator A | 2024-07-20 | 2024-08-15 | In Progress | $13,450.00
T1004 | Transportation Arrangements (Local) | Local Partner Team | 2024-08-10 | 2024-08-31 | Pending | $3,750.00
T1005 | Travel Insurance & Documentation Check | Admin Support Staff | 2024-07-28 | 2024-08-15 | In Progress | $1,950.00
T1006 | Itinerary Finalization & Client Approval | Project Manager - Client Liaison | 2024-08-25 | 2024-08-31 | Pending | $500.00
T1007 | Travel Execution & On-Site Coordination | Onsite Coordinator Team | 2024-09-01 | 2024-10-31 | Pending | $8,575.00
T1008 | Post-Trip Review & Reporting | Project Manager - Finance & Analysis | 2024-11-05 | 2024-11-30 | Pending | $750.00
Total Project Budget: | [5 empty] | $37,375.00
Notes:
This project plan is intended for client viewing only.
Progress updates will be provided every Friday via email.
All budget values are in USD and subject to change based on exchange rates and final booking confirmations.