## Worksheet
Travel Planning Project Plan (Detailed)
Task ID | Task Name | Description | Responsible Party | Start Date | End Date | Status | Priority
Phase 1: Destination Research & Initial Planning (Weeks 1-2)
T001 | Define Travel Objectives | Identify goals, budget range, travel duration and key interests. | Project Manager | 2024-05-27 | 2024-05-31 | In Progress | High
T002 | Select Target Destinations | Evaluate 3 potential destinations based on budget, season, safety and interests. | Travel Coordinator | 2024-05-31 | 2024-06-07 | Not Started | High
Phase 2: Logistics & Booking (Weeks 3-6)
T003 | Book Flights | Compare prices and secure round-trip tickets with preferred airlines. | Travel Coordinator | 2024-06-10 | 2024-06-17 | Not Started | High
T004 | Reserve Accommodations | Select and book hotels, Airbnb or rental properties based on location and budget. | Travel Coordinator | 2024-06-17 | 2024-06-21 | Not Started | High
Phase 3: Itinerary Development (Weeks 7-8)
T005 | Develop Daily Itinerary | Create a day-by-day schedule including activities, meals, and travel times. | Travel Planner | 2024-06-24 | 2024-07-01 | Not Started | Medium
Phase 4: Final Preparations (Weeks 9-10)
T006 | Confirm All Bookings | Verify flight, hotel, and activity reservations. | Project Manager | 2024-07-01 | 2024-07-05 | Not Started | High
Phase 5: Travel Execution & Post-Trip Review (Weeks 11-12)
T007 | Execute Travel Plan | Travel to destination and follow itinerary with real-time adjustments if needed. | All Team Members | 2024-07-15 | 2024-07-31 | Not Started | High
T008 | Gather Feedback & Document Lessons Learned | Collect team feedback and update planning templates for future trips. | Project Manager | 2024-08-01 | 2024-08-05 | Not Started | Medium
Total Tasks: |  |  | 8 tasks (4 High, 2 Medium, 2 Not Started)