## Travel Planning - Employee View
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
T001 | Destination Research & Approval | John Doe | Completed | 2023-10-01 | 2023-10-05 | $500.00
T002 | Flight Booking & Confirmation | Jane Smith | In Progress | 2023-10-06 | 2023-10-15 | $1,800.00
T003 | Accommodation Reservation | Mike Johnson | Pending Approval | 2023-10-10 | 2023-10-25 | $950.00
T004 | Local Transportation Arrangements | Sarah Lee | Not Started | 2023-10-18 | 2023-10-30 | $450.00
T005 | Meeting & Event Scheduling | Chris Brown | Not Started | 2023-10-20 | 2023-11-05 | $600.00
T999 | Final Travel Package Review & Approval | Team Lead | Not Started | 2023-11-06 | 2023-11-10 | $50.00
Total Project Budget: | [5 empty] | $4,350.00
Note:This is a sample project plan for employee travel planning. Please update status, dates, and budget as needed.