## Worksheet
Travel Planning Project Plan - Extended Version
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % CompleteDependencies
Phase 1: Destination Research & Planning (Weeks 1-2)
TASK-001 | Define travel purpose and objectives | Project Manager | 2023-10-05 | 2023-10-15 | In Progress85%N/A
TASK-002 | Identify potential destinations based on budget & interests | Travel Coordinator | 2023-10-05 | 2023-10-17 | In Progress95%TASK-001
TASK-003 | Analyze destination safety, climate, and cultural considerations | Research Analyst | 2023-10-18 | 2023-10-25 | To Do0%TASK-002
Phase 2: Logistics, Accommodation & Transportation (Weeks 3-5)
TASK-004 | Finalize destination and create travel itinerary | Travel Planner | 2023-10-18 | 2023-11-05 | To Do3%TASK-003, TASK-045
TASK-005 | Book international flights with return options | Travel Coordinator | 2023-11-06 | 2023-11-14 | To Do0%TASK-045, TASK-047
TASK-006 | Secure accommodation for full duration of trip | Travel Coordinator | 2023-11-08 | 2023-11-15 | To Do0%TASK-047, TASK-046
Phase 3: Document Collection & Pre-Trip Prep (Weeks 6-7)
TASK-007 | Obtain required visas and travel documents | Travel Coordinator | 2023-11-16 | 2023-11-30 | To Do0%TASK-045, TASK-047, TASK-048
TASK-008 | Confirm all bookings and collect e-tickets & vouchers | Project Manager | 2023-11-27 | 2023-12-05 | To Do5%TASK-046, TASK-047, TASK-058
MILESTONE-1 | Complete Pre-Trip Documentation & Bookings | Project Manager | 2023-12-05 | 2023-12-05 | In Progress98%TASK-046, TASK-047, TASK-058, TASK-119
Phase 4: Final Checks & Departure (Weeks 8-9)
TASK-009 | Prepare travel packing list and check essentials | All Team Members | 2023-12-06 | 2023-12-14 | To Do0%MILESTONE-1, TASK-049, TASK-55
TASK-010 | Update emergency contact information and travel insurance details | Project Manager | 2023-12-15 | 2023-12-17 | To Do0%TASK-49, TASK-67, TASK_98
MILESTONE-2 | Final Departure Readiness Confirmed | Project Manager | 2023-12-18 | 2023-12-18 | To Do0%TASK-55, TASK_98, TASK_96
Project Summary: | [6 empty] | Overall Progress: 12% Complete