## Worksheet
Task | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Status
Destination Research & Selection | 2024-01-15 | 2024-01-25 | 300 | 285.75 | In Progress
Flight Booking & Tickets | 2024-01-26 | 2024-01-31 | 850 | 875.5 | Over Budget
Lodging Reservations (Hotel & Rentals) | 2024-01-31 | 2024-02-15 | 1,450.00 | 1,398.75 | On Track
Local Transportation Arrangements | 2024-02-16 | 2024-03-10 | 375 | 365.95 | On Track
Travel Insurance & Documentation | 2024-01-20 | 2024-01-31 | 185 | 179.55 | On Track
Tour & Activity Bookings | 2024-02-16 | 2024-03-15 | 650 | 689.33 | Over Budget
Total Project Cost |  |  | 3,810.00 | 3,794.83 | Under Budget