## Travel Planning - Project Plan
Travel Planning - Project Plan (Large Business Style)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | Budget (USD)(Estimate)
T001 | Initial Planning & Requirements Gathering | Project Management Office | 2023-12-05 | 2023-12-15 | In Progress | $8,500.00(Estimated)
T002 | Destination Research & Selection | Travel Research Team | 2023-12-16 | 2024-01-15 | In Progress | $6,750.00(Estimated)
T003 | Flight Booking & Airfare Negotiation | Logistics & Procurement Team | 2024-01-16 | 2024-01-31 | Completed | $95,300.00(Actual)
T004 | Hotel & Accommodation Reservations | Facilities & Travel Team | 2024-01-16 | 2024-02-15 | In Progress | $78,950.00(Estimated)
T005 | Transportation & Ground Logistics Arrangement | Logistics Team | 2024-01-31 | 2024-02-15 | Delayed | $34,875.00(Estimated)
T006 | Itinerary Development & Finalization | Project Coordination Team | 2024-02-16 | 2024-03-15 | In Progress | $7,850.00(Estimated)
T007 | Travel Insurance & Risk Assessment | Risk Management Office | 2024-03-16 | 2024-3-31 | Completed | $5,975.00(Actual)
T008 | On-Site Coordination & Local Partner Contracts | Regional Operations Team | 2024-3-16 | 2024-4-30 | In Progress | $18,950.00(Estimated)
T009 | Final Preparations & Staff Briefing | Project Management Office | 2024-5-15 | 2024-5-31 | Delayed | $9,800.00(Estimated)
T010 | Travel Execution & Monitoring (On-site) | All Teams | 2024-6-15 | 2024-7-31 | In Progress | $38,500.00(Estimated)
T011 | Post-Travel Review & Reporting | Project Management Office | 2024-8-05 | 2024-8-31 | Completed | $6,750.00(Actual)
T012 | Cost Reconciliation & Financial Audit | Finance Department | 2024-9-01 | 2024-9-30 | In Progress | $7,550.00(Estimated)
Total Estimated Budget: | [5 empty] | $311,075.00(Sum of Estimates)