## Travel Planning - Project Plan
Travel Planning - Project Plan
Multi-Page Template ¦ Purpose: Travel Planning ¦ Version: 1.0
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
T01 | Determine Travel Destination & Dates | Project Manager | 2023-10-01 | 2023-10-05 | In Progress
T02 | Book Flights & Accommodations | Travel Coordinator | 2023-10-06 | 2023-10-15 | Pending
T03 | Prepare Travel Itinerary & Documents | Completed on 2023-10-18
T04 | Obtain Visas & Permits (if required) | Administrative Assistant | 2023-10-16 | 2023-10-25 | In Progress
T05 | Arrange Local Transportation & Tours | Not Started
Task ID | Budget Allocation | Actual Spend | Remaining Budget | Risk Level | Notes / Comments
T01 | $2,000.00 | $850.56 | $1,149.44 | Low | Destination finalized with good rates.
T02 | $3,500.00 | $2,875.33 | $624.67 | Medium | Flight prices fluctuating; monitored daily.
T03 | $1,200.00 | $1,198.95 | $1.05 | Low | Document processing completed within budget.
T04 | $800.00 | $324.71 | $475.29 | Medium | Visa application submitted; processing may extend timeline.
T05 | $2,000.00 | $- - - (Not Started) | $2,000.01 | High | Booking requires confirmation from local partners.
Meeting Date | Attendees | Agenda Item | Status Update | Action Items
2023-10-03 | PM, TC, AA | Determine Travel Goals & Timeline | Completed - Destination selected: Bali, Indonesia (Nov 5–15)
2023-10-10 | PM, TC | Review Flight Options & Accommodations | In Progress - Final options to be compared by Oct 14.
2023-10-17 | PM, AA, TC | VISA Processing & Document Check | Completed - All documents submitted; awaiting confirmation.
2023-10-24 | TBC (Next Week) | Draft Local Tour Schedule & Confirm Booking | Pending - Await response from tour providers.