## Travel Planning - Project Plan
Travel Planning - Project Plan
Office Use ¦ Version 1.0 ¦ Prepared for Project Management Team
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
T001 | Define travel objectives and scope | Project Manager | 2023-10-01 | 2023-10-05 | In Progress | $500.00
T002 | Research destination and visa requirements | Travel Coordinator | 2023-10-06 | 2023-10-15 | To Do | $350.00
T003 | Book flights and accommodation | Travel Coordinator | 2023-10-16 | 2023-10-25 | To Do | $4,800.00
T004 | Arrange local transportation and tours | Local Agent (Vendor) | 2023-10-26 | 2023-11-05 | To Do | $1,750.00
T005 | Prepare travel documents and insurance | Project Manager | 2023-11-06 | 2023-11-10 | To Do | $450.00
T006 | Conduct pre-travel briefing and safety training | HR & Safety Officer | 2023-11-11 | 2023-11-15 | To Do | $750.00
T007 | Travel execution and on-site coordination | Project Manager, Local Agent | 2023-11-16 | 2023-11-30 | To Do | $8,500.00
T008 | Post-travel evaluation and reporting | Project Manager, Analyst | 2023-12-01 | 2023-12-15 | To Do | $600.00
Total Estimated Budget:$18,750.00