## Travel Planning Project Plan
Travel Planning Project Plan
Task ID | Task Description | Assigned To | Start Date | End Date | Status
T001 | Research travel destinations and weather conditions | Alice Chen | 2024-04-05 | 2024-04-10 | In Progress
T002 | Book flights and accommodation (3-star hotels) | Brian Lee | 2024-04-11 | 2024-04-18 | Pending
T003 | Create daily itinerary and sightseeing plans | Claire Park | 2024-04-15 | 2024-04-19 | Pending
T004 | Obtain travel visas and necessary documentation | Daniel Kim | 2024-04-18 | 2024-04-25 | Pending
T005 | Arrange transportation (rental car & train passes) | Elena Rodriguez | 2024-04-19 | 2024-04-30 | Pending
T006 | Confirm all bookings and finalize budget allocation | Fiona Wong | 2024-05-15 | 2024-05-18 | Pending
T007 | Prepare travel packs and emergency kits | Gabriel Taylor | 2024-05-19 | 2024-05-23 | Pending
T008 | Final review and team briefing session | Hannah Patel | 2024-05-31 | 2024-06-03 | Pending