## Worksheet
Travel Planning Project Plan - Report Version
Phase | Task Description | Assigned To | Start Date | End Date | Status | Budget (USD)
Planning & Research | Identify travel destinations and seasonal considerations | Travel Coordinator | 2023-10-01 | 2023-10-15 | In Progress | $500.00
Planning & Research | Research visa requirements and travel documentation | Travel Coordinator | 2023-10-16 | 2023-10-25 | To Do | $300.00
Booking & Logistics | Book flights and accommodations based on budget constraints | Travel Coordinator, Finance Team | 2023-10-26 | 2023-11-05 | To Do | $4,500.00
Booking & Logistics | Arrange local transportation and tour guides | Local Liaison, Travel Coordinator | 2023-11-06 | 2023-11-15 | To Do | $800.00
Pre-Trip Preparation | Issue travel documents and insurance policies to participants | HR, Travel Coordinator | 2023-11-16 | 2023-11-25 | To Do | $600.00
Pre-Trip Preparation | Conduct pre-departure briefing session with team members | Project Manager, Team Lead | 2023-11-26 | 2023-11-30 | To Do | $150.00
On-Trip Execution | Oversee daily itinerary and ensure adherence to schedule | Project Manager, Travel Coordinator | 2023-12-01 | 2023-12-15 | To Do | $6,000.00
On-Trip Execution | Manage real-time issues and contingency responses | Project Manager, On-Site Lead | 2023-12-01 | 2023-12-15 | To Do | $750.00
Post-Trip Review | Capture feedback from participants and team members | Project Manager, HR Team | 2023-12-16 | 2023-12-25 | To Do | $400.00
Post-Trip Review | Finalize project report and present findings to stakeholders | Project Manager, Finance Lead | 2023-12-26 | 2024-01-05 | To Do | $800.00
Total Project Budget:$15,750.00
Note: This report version is intended for internal tracking and presentation purposes. All dates are subject to change based on external factors.