## Travel Planning Project Plan
Travel Planning Project Plan
Task ID | Task Name | Start Date | End Date | Status | Assigned To
T001 | Destination Research | 2024-04-01 | 2024-04-05 | To Do | Jane Smith
T002 | Flight Booking | 2024-04-15 | 2024-04-17 | In Progress | Mike Johnson
T003 | Hotel Reservation | 2024-04-16 | 2024-04-18 | In Progress | Jane Smith
T004 | Travel Insurance Purchase | 2024-04-19 | 2024-04-19 | Completed | Mike Johnson
T005 | Packing List Creation2024-04-252024-04-26To DoJane Smith
T006 | Visa Application (if required) | 2024-05-15 | 2024-05-31 | To Do | Mike Johnson
T007 Daily Itinerary Planning 2024-06-15 2024-06-18In ProgressJane Smith
T008 | Final Check & Departure Preparation | 2024-06-30 2024-07-15 To Do All Team Members