## Worksheet
Travel Planning - Project Plan
Startup Style ¦ Version 1.0 ¦ Updated: June 2024
Task ID | Task Name | Assigned To | Due Date | Status | Priority
T001 | Define travel objectives & budget | Alice Johnson | 2024-06-15 | In Progress | High
T002 | Research destination options (3 countries) | Michael Chen | 2024-06-18 | Pending | High
T003 | Book initial flights & accommodations | Sophia Martinez | 2024-06-25 | PendingMedium
T004 | Develop itinerary & daily schedule | Alice Johnson | 2024-06-28 | PendingMedium
T005 | Obtain travel insurance & visas | James Wilson | 2024-07-01 | PendingHigh
T006 | Arrange local transportation & guides | Sophia Martinez | 2024-07-05 | PendingMedium
T007 | Finalize budget & approve expenses | Alice Johnson | 2024-07-10 | PendingHigh
T008 | Conduct pre-trip briefing & team meeting | Michael Chen | 2024-07-15 | PendingMedium
T009 | Finalize travel documents & checklists | James Wilson | 2024-07-18 | PendingLow
T010 | Departure & on-trip monitoring | All Team Members | 2024-07-25 | PendingHigh