## Worksheet
Task | Start Date | End Date | Status | Assigned To | Priority
Destination Research | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith | High
Flight Booking | 2023-10-06 | 2023-10-10 | To Do | John Doe | High
Accommodation Reservation | 2023-10-07 | 2023-10-11 | To Do | Alice Johnson | Medium
Travel Insurance Purchase | 2023-10-08 | 2023-10-12 | To Do | Robert Brown | Medium
Itinerary Planning | 2023-10-13 | 2023-10-17 | To Do | Jane Smith | High
Passport & Visa Check | 2023-10-18 | 2023-10-20 | To Do | John Doe | High
Packing List Creation | 2023-10-21 | 2023-10-23 | To Do | Alice Johnson | Low
Final Travel Review & Approval | 2023-10-24 | 2023-10-25 | To Do | Robert Brown | High