## Travel Planning - Analysis View
Travel Planning - Analysis View
Project Phase | Task Description | Location | Date Range | Budget (USD) | Status | Responsible Team Member
Planning Phase
1. Initial Research | Identify potential travel destinations based on team preferences and budget constraints. | N/A | 2023-10-01 to 2023-10-15 | 500 | In Progress | Alice Johnson
2. Destination Evaluation | Evaluate top 3 destinations using criteria: cost, climate, safety, accessibility. | N/A | 2023-10-16 to 2023-10-25 | 750 | Not Started | Robert Smith
Booking Phase
3. Flight Reservations | Book round-trip flights for team members to selected destination. | Barcelona, Spain | 2023-11-05 to 2023-11-15 | 4,800.00 | Pending Approval | Sarah Williams
4. Accommodation Booking | Reserve hotel accommodations for the duration of the trip. | Barcelona, Spain | 2023-11-05 to 2023-11-15 | 3,600.00 | Pending Approval | Sarah Williams
Logistics Phase
5. Transportation Arrangements | Organize local transport (taxis, rental car, public transit passes). | Barcelona, Spain | 2023-11-05 to 2023-11-15 | 900 | Pending Approval | Liam Brown
6. Event & Activity Planning | Schedule team-building activities, sightseeing tours, and official meetings. | Barcelona, Spain | 2023-11-05 to 2023-11-15 | 1,800.00 | Pending Approval | Mia Davis
Final Phase (Pre-Departure)
7. Travel Documentation | Verify passports, visas, insurance policies, and vaccination records. | N/A | 2023-10-20 to 2023-11-04 | 350 | In Progress | Alice Johnson
Total Estimated Budget (USD) | $12,650.00