## Worksheet
Travel Planning - Large Business Project Template
Template Type:Project Template
Purpose:Travel Planning
Date Created:2024-04-30
Phase | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
1. Planning & Research | Define Travel Objectives and Scope | Project Manager | 2024-05-01 | 2024-05-05 | In Progress | $1,500
| Market Research & Destination Analysis | Research Team Lead | 2024-05-06 | 2024-05-13 | Pending Review | $3,800
| Initial Budget Estimation & Approval | Finance Manager | 2024-05-14 | 2024-05-17 | To Do | $5,300
2. Booking & Logistics | Flight Reservations (Round Trip) | Travel Coordinator | 2024-05-18 | 2024-05-21 | To Do | $9,750
| Hotel & Accommodation Booking | Travel Coordinator | 2024-05-18 | 2024-05-23 | To Do | $7,500
| Ground Transportation Arrangements | Logistics Officer | 2024-05-24 | 2024-05-31 | To Do | $3,800
| Insurance & Emergency Planning Setup | HR Specialist | 2024-05-18 | 2024-05-31 | To Do
3. Preparation & Training | Team Briefing Session (In-Person) | Project Manager | 2024-06-01 | 2024-06-05 | To Do
| 4. Execution & On-site Management | On-site Coordination & Daily Check-ins | Field Supervisor | 2024-06-15 | 2024-07-15 | To Do
|  | 5. Post-Trip Review & Reporting | Post-Travel Debrief Meeting | Project Manager | 2024-07-16 | 2024-07-19 | To Do
TOTAL BUDGET: | [5 empty] | $57,000