## Travel Planning - Manager View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Budget Allocated ($)
TPL-001 | Destination Research & Approval | Emma Reynolds | 2023-10-05 | 2023-10-12 | Completed | 500
TPL-002 | Flight Booking & Confirmation | Liam Carter | 2023-10-13 | 2023-10-15 | In Progress | 2800
TPL-003 | Hotel Reservation & Payment | Sophia Martinez | 2023-10-14 | 2023-10-17 | In Progress | 1500
TPL-004 | Transportation Arrangements (Local) | Noah Williams | 2023-10-16 | 2023-10-19 | Pending | 800
TPL-005 | Meeting Venue Booking & Setup | Ava Thompson | 2023-10-18 | 2023-10-21 | Pending | 650
TPL-006 | Travel Insurance & Documentation Review | Oliver Brown | 2023-10-19 | 2023-10-24 | Pending | 350
Total Budget Used: | [5 empty] | $6,600