## Worksheet
Travel Planning - One Page Project Template
Project Phase | Task Description | Responsible Person | Dates (Start - End) | Status
1. Planning & Research
Destination Selection | Research and finalize travel destination based on budget, season, and interests. | Jane Doe | 2023-10-01 - 2023-10-05 | In Progress
Itinerary Design | Create detailed daily plans including activities, meals, and transport. | John Smith | 2023-10-06 - 2023-10-15 | Not Started
2. Reservations & Logistics
Flight Booking | Secure round-trip flights with preferred departure/arrival times. | Alice Johnson | 2023-10-16 - 2023-10-25 | Not Started
Accommodation Booking | Reserve hotel or rental accommodation with required amenities. | Bob Wilson | 2023-10-18 - 2023-10-27 | To Do
3. Pre-Trip Preparation
Passport & Visas | Verify passport validity and apply for required visas. | Jane Doe | 2023-10-10 - 2023-10-14 | Completed
Travel Insurance | Purchase comprehensive travel insurance with medical coverage. | John Smith | 2023-10-15 - 2023-10-20 | In Progress
4. During Trip Management
Activity Execution | Carry out planned activities as per itinerary. | All Team Members | 2023-11-01 - 2023-11-10 | To Do
Daily Logs & Feedback | Document daily experiences, issues, and improvements. | Alice Johnson | 2023-11-01 - 2023-11-10 | To Do
5. Post-Trip Review
Expense Reconciliation | Compile and review all travel expenses vs. budget. | Bob Wilson | 2023-11-15 - 2023-11-20 | To Do
Project Debrief & Reporting | Host meeting to review trip success, challenges, and recommendations. | Jane Doe | 2023-11-25 - 2023-11-30 | To Do
Total Project Duration: |  |  |  | 2023-10-01 - 2023-11-30
This template is designed for one-page travel project planning, featuring a clean structure suitable for Excel-like visualization.