## Worksheet
Phase | Task Description | Responsible Person | Start Date | End Date | Status | Budget Allocation ($)
1. Planning & Research | Define travel objectives and destinations | Project Manager | 2023-10-01 | 2023-10-05 | In Progress | 50
| Research accommodation options and availability | Travel Coordinator | 2023-10-06 | 2023-10-10 | Pending | 75
| Analyze transportation options (flights, trains, etc.) | Logistics Specialist | 2023-10-11 | 2023-10-15 | Pending | 100
2. Booking & Reservations | Book flights and confirm tickets | Travel Coordinator | 2023-10-16 | 2023-10-20 | Pending | 850
| Reserve accommodations and confirm reservations | Travel Coordinator | 2023-10-17 | 2023-10-21 | Pending | 650
| Arrange ground transportation (rental car, shuttle) | Logistics Specialist | 2023-10-18 | 2023-10-22 | Pending | 450
3. Itinerary Development | Create daily itinerary with activities and meals | Project Manager | 2023-10-23 | 2023-10-27 | Pending | 150
| Include emergency contacts and local information | Project Manager | 2023-10-28 | 2023-10-31 | Pending | 75
4. Final Preparations | Confirm all bookings and update travel documents | All Team Members | 2023-11-01 | 2023-11-05 | Pending | 50
| Distribute final travel package (digital & print) | Travel Coordinator | 2023-11-06 | 2023-11-07 | Pending | 35
Total Budget: | [5 empty] | 2,985.00
Notes:
Update status weekly to track project progress.
All budget figures are in USD.
This template is designed for printing; ensure margins are set to standard (1 inch) for best results.