## Worksheet
Travel Planning Project Template
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
T001 | Destination Research & Selection | Jane Smith | Pending | 2025-04-05 | 2025-04-12 | $850.00
T002 | Flight Booking & Confirmation | Mike Johnson | In Progress | 2025-04-13 | 2025-04-18 | $1,750.00
T003 | Hotel Reservation & Confirmation | Sarah Lee | Pending | 2025-04-15 | 2025-04-19 | $3,400.00
T004 | Travel Insurance Purchase | David Brown | Pending | 2025-04-16 | 2025-04-17 | $380.00
T005 | Local Transportation Arrangements | Amy Garcia | Not Started | 2025-04-18 | 2025-04-19 | $650.00
T006 | Itinerary Development & Sharing | Jane Smith | Not Started | 2025-04-19 | 2025-04-19 | $150.00
T007 | Emergency Plan & Contact List Finalization | Mike Johnson | Not Started | 2025-04-19 | 2025-04-19 | $75.00
T008 | Final Travel Briefing & Team Meeting | All Team Members | Not Started | 2025-04-20 | 2025-04-21 | $100.00
Total Estimated Budget: | [5 empty] | $7,355.00