## Worksheet
Travel Planning - Project Template - Report Version
Task ID | Activity/Item | Responsible Person | Start Date | End Date | Status | Budget (USD)
TPL-001 | Destination Research & Selection | Emma Thompson | 2024-10-15 | 2024-10-25 | In Progress | $850.00
TPL-002 | Flight Booking & Confirmation | James Reed | 2024-10-26 | 2024-11-03 | Pending Approval | $1,675.50
TPL-003 | Hotel Reservation & Contract Review | Sarah Collins | 2024-11-04 | 2024-11-15 | Not Started | $3,890.00
TPL-004 | Visa & Travel Document Processing | Liam Foster | 2024-11-16 | 2024-11-30 | Not Started | $650.00
TPL-005 | Local Transportation Arrangements | Olivia Bennett | 2024-12-01 | 2024-12-15 | Not Started | $980.75
TPL-006 | Activity & Excursion Planning | Mia Rodriguez | 2024-12-16 | 2025-01-15 | Not Started | $1,745.00
TPL-007 | Insurance & Emergency Planning | Noah Carter | 2024-12-16 | 2025-01-31 | Not Started | $456.30
Total Estimated Budget: | [5 empty] | $9,247.55
Report generated on October 10, 2024 ¦ This document is for internal use only.