## Worksheet
Travel Planning - Small Business Project Template
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
T001 | Define travel purpose and objectives | Project Manager | 2023-10-01 | 2023-10-05 | In Progress
T002 | Identify destinations and key stakeholders | Travel Coordinator | 2023-10-06 | 2023-10-15 | To Do
T003 | Research transportation options and costs | Finance Officer | 2023-10-16 | 2023-10-25 | To Do
T004 | Book flights and accommodations | Travel Coordinator | 2023-10-26 | 2023-11-05 | To Do
T005 | Prepare travel itineraries and documentation | Project Manager | 2023-11-06 | 2023-11-15 | To Do
T006 | Conduct pre-travel briefing with team members | Project Manager | 2023-11-16 | 2023-11-20 | To Do
T007 | Execute travel plan and monitor progress | Travel Coordinator | 2023-11-21 | 2023-12-05 | To Do
T008 | Collect feedback and evaluate travel outcomes | Project Manager | 2023-12-06 | 2023-12-15 | To Do
Notes:
Use this template to track all aspects of business travel planning.
Status options: To Do, In Progress, Completed.
Update task status regularly to ensure project visibility and accountability.