## Worksheet
Travel Planning - Team Use Project Template
Task ID | Task Name | Description | Assigned To | Status | Due Date | Budget (USD)
T001 | Destination Research | Analyze top travel destinations based on team preferences and budget. | Team A | Not Started | 2023-10-15 | $500.00
T002 | Flight Booking | Secure round-trip flights for all team members. | Team B | In Progress | 2023-10-25 | $1,800.00
T003 | Accommodation Booking | Reserve hotel rooms for the entire team. | Team C | In Progress | 2023-10-28 | $1,500.00
T004 | Local Transportation Plan | Arrange rental cars and transit options for the stay. | Team D | Pending Approval | 2023-11-05 | $400.00
T005 | Itinerary Development | Create daily schedule with activities and meetings. | Team A | Not Started | 2023-11-10 | $0.00
T006 | Daily Expenses Forecasting | Estimate food, entertainment, and incidentals per day. | Team B | In Progress | 2023-11-15 | $750.00
T007 | Team Briefing Session | Conduct pre-travel meeting to review plans and roles. | Team Lead | Scheduled | 2023-11-20 | $0.00
Total Estimated Budget: | [5 empty] | $5,950.00