## Worksheet
Travel Planning - Project Timeline
Task ID | Task Description | Responsible Team Member | Start Date | End Date | Status | Prioritization Level
#T001 | Destination Research & Selection | Emily Chen | 2024-11-05 | 2024-11-15 | In Progress | High
#T002 | Flight Booking & Confirmation | James Rodriguez | 2024-11-16 | 2024-11-30 | Pending | High
#T003 | Accommodation Reservation | Laura Mitchell | 2024-11-18 | 2024-12-05 | Pending | High
#T004 | Travel Insurance Purchase | David Kim | 2024-11-25 | 2024-11-30 | Pending | Medium
#T005 | Visa & Documentation Processing | Sophie Williams | 2024-11-10 | 2024-12-15 | In Progress | High
#T006 | Itinerary Development & Sharing | Emily Chen | 2024-12-16 | 2024-12-30 | Pending | Medium
#T007 | Local Transportation Arrangements | James Rodriguez | 2024-12-18 | 2025-01-15 | Pending | Medium
#T008 | Emergency Kit & Medical Prep | Laura Mitchell | 2024-12-25 | 2025-01-10 | Pending | Low
#T009 | Final Travel Briefing Session | Sophie Williams | 2025-01-16 | 2025-01-18 | Pending | Medium
#T010 | Post-Trip Feedback & Documentation | All Team Members | 2025-01-25 | 2025-02-15 | Pending | Low
Last Updated: November 5, 2024 ¦ Project Duration: November 5, 2024 – February 15, 2025