## Worksheet
Travel Planning Project Timeline
Task ID | Task Description | Start Date | End Date | Status | Assigned To
T001 | Define travel objectives and budget | 2023-10-05 | 2023-10-10 | In Progress | Jane Smith
T002 | Select destination and travel dates | 2023-10-11 | 2023-10-15 | Not Started | Mike Johnson
T003 | Milestone: Destination Finalized | 2023-10-15 | 2023-10-15 | Not Started | N/A
T004 | Book flights and accommodations | 2023-10-16 | 2023-10-25 | Not Started | Sarah Lee
T005 | Obtain travel visas and documents | 2023-10-18 | 2023-10-30 | Not Started | David Brown
T006 | Milestone: All Bookings Confirmed | 2023-10-25 | 2023-10-25 | Not Started | N/A
T007 | Create travel itinerary and packing list | 2023-10-26 | 2023-11-01 | Not Started | Jane Smith
T008 | Arrange transportation and activities at destination | 2023-11-02 | 2023-11-10 | Not Started | Mike Johnson
T009 | Milestone: Travel Plan Complete | 2023-11-10 | 2023-11-10 | Not Started | N/A
T010 | Final review and approval of travel plan | 2023-11-11 | 2023-11-15 | Not Started | Sarah Lee
T011 | Departure and travel execution | 2023-11-16 | 2023-11-30 | Not Started | All Team Members
T012 | Milestone: Travel Complete and Debriefing | 2023-11-30 | 2023-12-05 | Not Started | All Team Members