## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Duration (Days)(Est.)
Planning Phase (Weeks 1-4)
T01 | Define travel purpose and objectives | 2025-04-01 | 2025-04-03 | In Progress | Jane Smith | 3(Est.)
T02 | Establish travel budget and allocate funds | 2025-04-01 | 2025-04-05 | In Progress | John Doe | 5(Est.)
T03 | Select destination(s) and finalise travel dates | 2025-04-06 | 2025-04-10 | Not Started | Sarah Lee | 5(Est.)
Booking Phase (Weeks 5-8)
T04 | Book flights and confirm departure/arrival times | 2025-04-11 | 2025-04-18 | Not Started | Jane Smith | 8(Est.)
T05 | Reserve accommodations and confirm check-in/out dates | 2025-04-13 | 2025-04-21 | Not Started | John Doe | 9(Est.)
T06 | Arrange ground transportation (rental car, local transit) | 2025-04-14 | 2025-04-19 | Not Started | Sarah Lee | 6(Est.)
Preparation Phase (Weeks 9-12)
T07 | Obtain necessary travel documents (visas, insurance, etc.) | 2025-04-22 | 2025-04-30 | Not Started | Jane Smith | 9(Est.)
T08 | Pack and organize travel essentials (clothing, electronics, documents) | 2025-05-01 | 2025-05-06 | Not Started | All Team Members | 6(Est.)
Travel Execution Phase (Week 13-20)
T09 | Departure: Fly to destination city | 2025-05-14 | 2025-05-14 | Milestone Reached | All Team Members | 1(Est.)
T10 | Attend scheduled meetings and events at destination (Day 1-7) | 2025-05-15 | 2025-05-21 | Not Started | All Team Members | 7(Est.)
Return Phase (Week 21)
T11 | Return: Fly back to home city | 2025-05-26 | 2025-05-26 | Milestone Reached | All Team Members | 1(Est.)
Post-Trip Phase (Week 22-24)
T12 | Submit travel expense reports and documentation | 2025-05-30 | 2025-06-04 | Not Started | Jane Smith | 6(Est.)
T13 | Capture lessons learned and prepare post-trip report | 2025-06-05 | 2025-06-11 | Not Started | All Team Members | 7(Est.)
T14 | Final Project Closure: Complete all deliverables and close project file | 2025-06-12 | 2025-06-15 | Milestone Not Started | Jane Smith (Lead) | 4(Est.)