## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Priority
Destination Research & Selection | 2023-10-01 | 2023-10-05 | 5 | Jane Doe | In Progress | High
Flight Booking & Confirmation | 2023-10-06 | 2023-10-10 | 5 | John Smith | Pending | High
Accommodation Reservation | 2023-10-08 | 2023-10-15 | 8 | Jane Doe | In Progress | High
Travel Insurance Purchase | 2023-10-11 | 2023-10-12 | 2 | Alice Brown | Completed | Medium
Visa & Document Preparation | 2023-10-13 | 2023-10-18 | 6 | Michael Lee | Pending | High
Itinerary Finalization & Sharing | 2023-10-19 | 2023-10-20 | 2 | Jane Doe | Pending | Medium
Travel Packing & Preparation | 2023-10-21 | 2023-10-30 | 10 | All Team Members | Pending | Medium
Departure & Travel Phase (Trip) | 2023-10-31 | 2023-11-15 | 16 | All Team Members | Pending | High
Post-Trip Debrief & Feedback Collection | 2023-11-16 | 2023-11-20 | 5 | Jane Doe | Pending | Low
Total Duration: |  |  | 67 days