## Worksheet
Travel Planning - Project Timeline (Manager View)
Task | Start Date | End Date | Status | Priority | Responsible Team Member(s)
Phase 1 - Planning & Research
Define travel objectives and budget | 2024-11-01 | 2024-11-05 | In Progress | High | Alice Johnson, Mark Reed
Research destination options and visa requirements | 2024-11-06 | 2024-11-15 | Pending | High | Sophie Liu, James Wilson
Phase 2 - Logistics & Booking
Book flights and accommodations | 2024-11-16 | 2024-11-30 | Pending | High | Robert Kim, Emily Chen
Arrange transportation and local activities | 2024-11-20 | 2024-12-05 | Pending | Medium | David Patel, Laura Smith
Phase 3 - Final Preparations
Issue travel documents and confirm bookings | 2024-12-06 | 2024-12-10 | Pending | High | Alice Johnson, Robert Kim
Final team briefing and travel pack distribution | 2024-12-11 | 2024-12-15 | Pending | Medium | Mark Reed, Emily Chen
Phase 4 - On-Travel & Reporting
Execute travel plan and monitor progress | 2024-12-16 | 2025-01-03 | Pending | High | All Team Members (Field)
Submit post-travel report and feedback | 2025-01-04 | 2025-01-10 | Pending | Medium | Alice Johnson, James Wilson
Last updated on December 5, 2024 ¦ Manager View – Travel Planning Project Timeline