## Worksheet
Task | Start Date | End Date | Status | Responsible Team Member | Budget Allocation (USD)
Destination Research & Selection | 2024-01-15 | 2024-01-30 | In Progress | Jane Smith | $850.00
Flight Booking & Itinerary Confirmation | 2024-02-01 | 2024-02-15 | Pending | Mark Johnson | $3,450.00
Hotel & Accommodation Reservations | 2024-02-16 | 2024-03-15 | Pending | Lisa Chen | $5,800.00
Travel Insurance & Documentation | 2024-03-16 | 2024-03-31 | Pending | Ryan Davis | $650.00
Local Transportation Arrangements | 2024-04-01 | 2024-04-15 | Pending | Sarah Lee | $1,350.00
Activity & Tour Booking (Sightseeing) | 2024-04-16 | 2024-05-15 | Pending | Alex Rodriguez | $3,750.00
Final Pre-Trip Briefing & Check-In | 2024-05-16 | 2024-05-31 | Pending | Jane Smith | $250.00
Total Project Cost |  |  |  |  | $15,300.00