## Worksheet
Travel Planning - Project Timeline (Planning View)
Task | Start Date | End Date | Status | Assigned To | Description
Project Kickoff & Goal Setting | 2024-01-05 | 2024-01-07 | Completed | Team Lead | Define travel purpose, budget, duration and key objectives.
Destination Research & Selection | 2024-01-08 | 2024-01-15 | In Progress | Research Team | Evaluate top 3 destinations based on budget, weather, and interests.
Itinerary Development | 2024-01-16 | 2024-01-25 | Not Started | Tour Planner | Create detailed daily plans including activities, meals, and transit.
Flight & Accommodation Booking | 2024-01-18 | 2024-01-30 | Not Started | Booking Coordinator | Secure flights, hotel reservations, and transportation options.
Travel Documents & Insurance | 2024-01-31 | 2024-02-05 | Not Started | Tour Planner | Obtain passports, visas, travel insurance, and vaccination records.
Final Review & Approval | 2024-02-06 | 2024-02-10 | Not Started | Team Lead | Review full itinerary, confirm all arrangements, and approve final plan.
Travel Departure | 2024-02-11 | 2024-02-18 | Not Started | All Team Members | Depart for destination; begin on-site travel activities.
Return & Debrief | 2024-02-19 | 2024-02-23 | Not Started | All Team Members | Return home and conduct post-trip evaluation meeting.
Note: This timeline is a high-level planning view. Adjust dates and tasks based on actual progress.