## Worksheet
Travel Planning Project Timeline
Phase | Task Description | Start Date | End Date | Status
Planning & Research | Define travel destination and purpose of trip | 2024-04-01 | 2024-04-07 | Complete
Budgeting & Financing | Estimate travel budget (flights, accommodation, food) | 2024-04-08 | 2024-04-15 | Complete
| Secure funding or approval from stakeholders | 2024-04-16 | 2024-04-23 | In Progress
| Finalize budget and reserve funds | 2024-04-24 | 2024-05-01 | Pending
Logistics & Booking | Book flights and confirm departure/arrival times | 2024-05-02 | 2024-05-15 | Pending
| Reserve accommodations and confirm details | 2024-05-16 | 2024-05-31 | Pending
| Arrange local transportation and activities | 2024-06-01 | 2024-06-15 | Pending
Pre-Trip Preparation | Obtain necessary travel documents (passports, visas) | 2024-06-16 | 2024-07-15 | Pending
Final Review & Departure | Confirm all bookings and prepare travel kit | 2024-07-16 | 2024-07-31 | Pending