## Worksheet
Task | Start Date | End Date | Status | Responsible Person
Define Travel Goals & Budget | 2024-01-15 | 2024-01-20 | In Progress | Jane Doe
Research Destinations & Itineraries | 2024-01-21 | <2024-01-31 | Pending | John Smith
Book Flights & Accommodations | 2024-02-01 | 2024-02-15 | Pending | Maria Lopez
Arrange Local Transportation & Tours | 2024-02-16 | 2024-03-01 | Pending | David Kim
Create Detailed Travel Schedule & Share with Team | 2024-03-02 | 2024-03-15 | Pending | Jane Doe
Finalize Budget Approval & Confirm Expenses | 2024-03-16 | 2024-03-25 | Pending | Maria Lopez
Travel Preparations (Visas, Insurance, etc.) | 2024-03-18 | 2024-04-15 | Pending | John Smith
Departure & Travel Period (Main Trip) | 2024-04-16 | 2024-05-31 | Pending | All Team Members
Post-Trip Review & Reporting | 2024-06-01 | 2024-06-15 | Pending | Jane Doe & David Kim
Note: This timeline is a sample for small business travel planning. Adjust dates and tasks as needed.