## Worksheet
Travel Planning - Project Timeline (Summary View)
Phase | Task | Start Date | End Date | Status | Responsible Party
Planning & Preparation Phase
1. Destination Selection | Research and finalize travel destination | 2024-01-05 | 2024-01-15 | In Progress | Jane Doe
2. Budget Planning | Establish travel budget and cost estimates | 2024-01-10 | 2024-01-20 | In Progress | John Smith
Booking & Logistics Phase
3. Flight Booking | Reserve flights with preferred airline and dates | 2024-01-18 | 2024-01-25 | Pending | Jane Doe
4. Accommodation Reservation | Book hotel or rental accommodation | 2024-01-20 | 2024-01-30 | Pending | John Smith
Travel Execution Phase
5. Travel Document Prep | Obtain visas, passports, insurance, and travel documents | 2024-01-25 | 2024-01-31 | Pending | Sarah Lee
6. Packing & Final Checks | Prepare luggage and confirm all travel essentials | 2024-02-01 | 2024-02-05 | Pending | All Team Members
On-the-Ground & Post-Trip Phase
7. In-Travel Coordination | Manage real-time travel adjustments and local logistics | 2024-02-10 | 2024-02-18 | Pending | Jane Doe, John Smith
8. Post-Trip Review & Reporting | Compile travel report and feedback summary | 2024-02-19 | 2024-02-25 | Pending | Sarah Lee
Note:This timeline provides a high-level overview for travel planning. Adjust dates and responsibilities as needed.